## Sheet1
Shade America Inc
Date | Day | Josh & Crew | Justin & Crew | LR & Crew | State/City
Holding Area
|  | Kompan-Spring Hills ES hang 2 shades 6001 Mariner Blvd. Spring Hill FL 34609 josh has permit docs. Josh Jordan Sky | Windmill-11865 Starbright Path Venice FL 34293 big job. Set 15 shade poles and 6 cantilever poles, 36'' auger. Waiting on Ricardo to schedule with us as 4-30 | Lake Mattie- 2590 Canvas Back Circle Auburndale, Fl 33823 Install shade when received per Brad. See May 25 on schedule
|  | Thrive-Ft. Lauderdale LR, Sam,Jordan,Josh Sr. Return to hang shade | Lakeside Sunstone Scott Carpenter sais working on revised engineering etc. get back on schedule to finish. Josh, Jordan, Sky | Jax Autism School- hang sail when it arrives to shop, follow up with Michelle on revising estimate and looking at additional work she wants done.
2026-05-01 | Fri | Gracewater order poles this day
2026-05-02 | Sat
2026-05-03 | Sun
2026-05-04 | Mon | Challenger K-8 hip badge job, set upper frame/fabric, picking uo shade friday.Has to be Jordan,Sky, Josh | Bliss- Lakeshore Park- hang 1 shade 8501 S Sherman Cir Miramar, FL 33025 Justin, Skip | Douglas-Selman set 6 poles to be pick up from steven 4-27, 2nd trip in June to hang shade LR, Sam, needs 30'' auger |  | Willis Elementary 14705 The Masters Ave. Bradenton, FL 34202 need too schedule final. skip has permit docs.
2026-05-05 | Tue |  | River Glen - 300 NW 45th Ave eerfield Beach FL hang 2 shades
2026-05-06 | Wed |  | Fleming Island repair, hang repaired shade
2026-05-07 | Thu
2026-05-08 | Fri
2026-05-09 | Sat
2026-05-10 | Sun
2026-05-11 | Mon |  | Aquatic Install-Do not move.
2026-05-12 | Tue
2026-05-13 | Wed
2026-05-14 | Thu
2026-05-15 | Fri |  |  |  |  | skip off 16-23
2026-05-16 | Sat |  |  |  | skip off
2026-05-17 | Sun
2026-05-18 | Mon | Gracewater-set poles |  | Kenly Park Set beams, upper frame and fabric, fabric ordered. 3101 N 66th St. Tampa, FL Do not move. Josh Sky, skip has permit docs
2026-05-19 | Tue
2026-05-20 | Wed
2026-05-21 | Thu |  | James Off
2026-05-22 | Fri |  |  |  |  | me off
2026-05-23 | Sat |  |  |  |  | skip off
2026-05-24 | Sun
2026-05-25 | Mon | Whitehead- Lake Mattie 2590 Canvas Back Ln. hang share hyperbolic Auburndale, FL 33823 Justin Skip do not move |  | Windward- Longleaf 11130 Longleaf Pines Bllvd. Sarasota, FL 34241 2-16 x 10 purlin hip call frank back on this date for update, problems and delays. Poles at PC | O.L. Peacock install extensions and shade1999 SW Dreyfus Blvd #1975 Port St Lucie, FL LR, Sam, Josh return end of may per grant
2026-05-26 | Tue
2026-05-27 | Wed
2026-05-28 | Thu
2026-05-29 | Fri
2026-05-30 | Sat
2026-05-31 | Sun
2026-06-01 | Mon | Kompan- Bethehem Christin Academy projected start date 544 Christian Ave Bethlehem , GA 30620 |  | Kompan-Hagen Park 1937 Wilton Dr. Ft. Lauderdale FL 6 post 3 sails |  | ultra sound 2:00 baptist old st aug.
2026-06-02 | Tue
2026-06-03 | Wed
2026-06-04 | Thu |  |  |  |  | cobb 10
2026-06-05 | Fri
2026-06-06 | Sat
2026-06-07 | Sun
2026-06-08 | Mon | Kompan-St Patrick
2026-06-09 | Tue
2026-06-10 | Wed
2026-06-11 | Thu |  |  |  |  | skip off
2026-06-12 | Fri
2026-06-13 | Sat
2026-06-14 | Sun
2026-06-15 | Mon
2026-06-16 | Tue
2026-06-17 | Wed
2026-06-18 | Thu
2026-06-19 | Fri
2026-06-20 | Sat
2026-06-21 | Sun
2026-06-22 | Mon
2026-06-23 | Tue
2026-06-24 | Wed
2026-06-25 | Thu
2026-06-26 | Fri
2026-06-27 | Sat
2026-06-28 | Sun
2026-06-29 | Mon
2026-06-30 | Tue
2026-07-01 | Wed
2026-07-02 | Thu
2026-07-03 | Fri
2026-07-04 | Sat
2026-07-05 | Sun
2026-07-06 | Mon | Windward-Palm Grovef Set beams/fabric 5800 Lakewood Ranch Blvd. N. Sarasota, Fl. 34240 Skip Justin Josh Sr. Inspection by Contractor. start fabrication of beams and elbows July 6th
2026-07-07 | Tue
2026-07-08 | Wed
2026-07-09 | Thu |  |  |  |  | skip off
2026-07-10 | Fri
2026-07-11 | Sat
2026-07-12 | Sun
2026-07-13 | Mon
2026-07-14 | Tue
2026-07-15 | Wed
2026-07-16 | Thu
2026-07-17 | Fri
2026-07-18 | Sat
2026-07-19 | Sun
2026-07-20 | Mon
2026-07-21 | Tue
2026-07-22 | Wed
2026-07-23 | Thu
2026-07-24 | Fri
2026-07-25 | Sat
2026-07-26 | Sun
2026-07-27 | Mon
2026-07-28 | Tue
2026-07-29 | Wed
2026-07-30 | Thu
2026-07-31 | Fri
2026-08-01 | Sat
2026-08-02 | Sun
2026-08-03 | Mon
2026-08-04 | Tue
2026-08-05 | Wed | Windward-Palm Grove-Install beams frames and fabric. Aug. 5th
2026-08-06 | Thu
2026-08-07 | Fri
2026-08-08 | Sat
2026-08-09 | Sun